## Sheet1
| Web App Lotus | Start Date (est) | 2021-09-01
No. | Task | September |  |  |  | Oktober |  |  |  | November
|  | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4
1 | Analisa dan Perancangan Sistem
ANALISA FLOW BISNIS | bar: September 1
PERANCANGAN DATABASE | bar: September 1
PERANCANGAN TAMPILAN DAN FLOW | bar: September 1
2 | Implementasi Bagian User
LOGIN | bar: September 1
REGISTER | bar: September 1
FORGOT PASSWORD | bar: September 2
PROFILE | bar: September 2
KYC (IDENTITY VERIFICATION) | bar: September 2
TRANSACTION PIN | bar: September 2
TRADING FUND (DEPOSIT) | bar: September 3
CREATE MT4 API ACCOUNT (VIA API) | bar: September 3
INTERNAL TRANSFER (VIA API) | bar: September 3
DOWNLINE (TREEVIEW) | bar: September 4
TICKET SUPPORT | bar: September 4
COMMISSION ROBOT SALES | bar: September 4
COMMISSION PROFIT SHARING | bar: Oktober 1 to Oktober 2
COMMISSION GROUP PROFIT SHARING | bar: Oktober 2 to Oktober 3
WITHDRAWAL | bar: Oktober 3
3 | Implementasi Bagian Mahasiswa
MANAGE ADMIN USER | bar: Oktober 4
MANAGE MEMBERS | bar: Oktober 4
MANAGE EXCHANGER | bar: Oktober 4
MANAGE DEPOSIT (FUND REQUEST) | bar: November 1
MANAGE WITHDRAWAL | bar: November 1
MANAGE KYC | bar: November 1
MANAGE BANK CRYPTO REQUEST | bar: November 1
MANAGE MT4 ACCOUNTS | bar: November 2
TRANSACTION HISTORY (WALLET AND COMMISSION) | bar: November 2
MT4 DEPOSIT (INTERNAL TRANSFER) | bar: November 2
MT4 WITHDRAWAL (INTERNAL TRANSFER) | bar: November 2
COMMISSION ROBOT SALES REPORT | bar: November 3
COMMISSION PROFIT SHARING REPORT | bar: November 3 to November 4
COMMISSION GROUP PROFIT SHARING REPORT | bar: November 4